## Sheet1
Start Date | Due Date | 2023 | Jan | Feb | Mar | Apr | May |  | Jun | July | Aug | Sep | Oct | Nov
2023-01-01 | 2023-01-31 | ‎Reaching out to health experts to lecture in YT educational videos
2023-01-01 | 2023-02-28 | Develop campaign with non-profits
2023-02-01 | 2023-03-31 | Producing YT videos/Coordinate with news outlets for promotional articles
2023-01-15 | 2023-03-31 | Develop anniversary blind box
2023-01-15 | 2023-02-15 | Develop app feature for "Check Your Chest" Challenge
| 2023-04-01 | Finalizing and scheduling YT videos and social media posts |  |  |  | ¦
2023-05-01 | 2023-05-10 | Release teasers on social media
| 2023-05-11 | Social Media: First-day release: Announcement of Savage X Breast Cancer Awareness News articles come out | [5 empty] | ¦
| 2023-05-12 | Social Media: "Check Your Chest" challenge, How to perform breast self-exam, 1YT educational video | [5 empty] | ¦
| 2023-05-13 | 2nd YT Video | [5 empty] | ¦
| 2023-05-14 | 3rd YT Video | [5 empty] | ¦
| 2023-05-19 | 4th YT Video | [5 empty] | ¦
| 2023-05-19 | Announce donation to breast cancer research and non-profits | [5 empty] | ¦
| 2023-06-11 | Announcing first month's "Check Your Chest" challenge winner | bar: Jun
| 2023-07-11 | Announcing second month's "Check Your Chest" challenge winner | bar: July
| 2023-08-11 | Announcing third month's "Check Your Chest" challenge winner | bar: Aug
| 2023-09-12 | Announcing fourth month's "Check Your Chest" challenge winner | bar: Sep
| 2023-10-11 | Announcing fifth month's "Check Your Chest" challenge winner with Breast Cancer Awareness Month Theme | bar: Oct
| 2023-11-11 | Announcing sixth month's "Check Your Chest" challenge winner, send out gifts for customers who kept the habit for six months | bar: Nov